## Arabic Translation
نوبل وودز للتجارة — تحليل الفجوات: المتطلبات التجارية والحلول (ترجمة عربية)
Odoo 19 Enterprise ¦ العراق ¦ 3 شركات ¦ 18 مستخدم
المرجع | النطاق | الاحتياج التجاري | الحل المقترح | المرحلة | النوع | الجهد | ملاحظات تقنية
0. نظرة عامة على الشركة والجوانب العامة
GEN-01 | عام | شركة نوبل وودز للتجارة شركة متخصصة في تجارة الأخشاب وتشغيلها داخل العراق، وتتعامل مع درجات متعددة من الأخشاب من مصادر دولية مختلفة، وتبيع للجملة والمفرد والمشاريع، ولديها أيضًا قسم تشغيل يعتمد على القص والتشكيل والتشطيب. معطيات المشروع: 3 شركات قانونية، 25 موظفًا / 18 مستخدم نظام، نظام سابق محلي، الاستضافة على Odoo.sh، والعمل باللغتين العربية والإنجليزية داخل العراق. | تهيئة بيئة متعددة الشركات داخل أودو لثلاث شركات مع دليل حسابات وإعدادات عملة وصلاحيات مستقلة لكل شركة، وتجهيز بيئة Odoo.sh مع فرعي staging وproduction. كذلك تثبيت العربية والإنجليزية وإعداد النماذج المطبوعة مثل الفواتير وأوامر الشراء والتسليم بشكل ثنائي اللغة لكل شركة. | المرحلة 1 | قياسي
GEN-02 | عام | يجب أن يدعم النظام 3 كيانات قانونية: الشركة A والشركة B كموردتين وتحملان المخزون، والشركة C كواجهة البيع الرئيسية للعملاء وغالبًا لا تحمل مخزونًا. المطلوب: صلاحيات حسب الشركة، فصل آمن للبيانات، كتالوج منتجات مشترك عند الحاجة، محاسبة مستقلة لكل شركة، وقواعد تعامل بين الشركات مع قيود رؤية حسب المستخدم. | يتم إنشاء كل شركة ككيان مستقل في إعدادات أودو، مع ضبط صلاحيات مبنية على الأدوار بحيث يرى كل مستخدم فقط الشركة أو الشركات المرتبطة بعمله. كما يتم تفعيل مشاركة كتالوج المنتجات بين الشركات عند الحاجة، ومراجعة قواعد التعامل بين A وB وC ثم إعدادها حسب سير العمل المتفق عليه. | المرحلة 1 | قياسي
1. البيانات الرئيسية وإعداد المنتج
MD-01 | المخزون / المبيعات | منتجات الأخشاب تُشترى وتُباع وتُخزن بوحدات قياس متعددة مثل المتر والربطة والقدم المكعب، ولكل منتج معامل تحويل خاص به بين الوحدات، ويجب أن يؤثر ذلك على سعر البيع والتكلفة وكميات المخزون. كما يجب إظهار الوحدة الثانوية في أوامر الشراء وتمكين عرض تقارير المخزون بأي وحدة مهيأة. | يتطلب ذلك تطويرًا مخصصًا لأن أودو القياسي يدعم معامل تحويل واحدًا عامًا لكل فئة وحدات. سيتم إضافة جدول تحويل وحدات على مستوى المنتج، وتحديد الوحدة وسعرها المرتبط، وإظهار الوحدة الثانوية والكمية المحولة في سطور الشراء، وتوسيع تقارير المخزون لدعم العرض المتعدد للوحدات. | المرحلة 1 | تطوير | 4
MD-02 | المخزون | كل منتج خشبي يُصنف إلى درجات جودة A وB وC. جميع الدرجات لها نفس تكلفة الشراء لكن أسعار بيع مختلفة، كما أن كمية كل درجة لا تكون معروفة عند الشراء بل تُحدد بعد التفريغ الفعلي في مستودع الفرز. | سيتم استخدام اللوتات لتتبع الدرجات، مع إنشاء نموذج يحدد الدرجة ومعاملها. تُعيّن الدرجة يدويًا لكل لوت عند الاستلام، وعند البيع يتم تطبيق معامل الدرجة على السعر بعد تحديد اللوت. | المرحلة 1 | تطوير | 2
MD-03 | المخزون / المبيعات | للمنتجات الخشبية متغيرات أبعاد متعددة مثل الطول والسماكة والعرض، إضافة إلى متغيرات اللون ضمن نفس قالب المنتج. | يتم تفعيل متغيرات المنتجات في أودو وإنشاء السمات المطلوبة مثل الطول والسماكة والعرض واللون، ثم ربطها بقوالب المنتجات لتوليد التراكيب المطلوبة من المتغيرات. | المرحلة 1 | قياسي
MD-04 | المخزون / المحاسبة | يجب احتساب متوسط التكلفة على مستوى قالب المنتج باحتساب جميع المتغيرات التابعة له مرجحةً بحسب الكميات الموجودة من كل متغير. أودو القياسي يحسب AVCO على مستوى المتغير فقط. | يستلزم ذلك تطوير حقل جديد على المنتج لعرض متوسط تكلفة مجمع على مستوى القالب بدل مستوى المتغير فقط. | المرحلة 1 | تطوير | 0.25
MD-05 | المشتريات | يجب أن يكون لكل مورد اسمان: اسم مستعار يظهر لجميع المستخدمين في أوامر الشراء والمستندات، واسم حقيقي يظهر فقط للمستخدمين ذوي الصلاحيات الإدارية لحماية سرية علاقات الموردين. | سيتم إضافة حقل للاسم الحقيقي للمورد في بطاقة المورد، مع تطبيق صلاحيات على مستوى الحقل بحيث لا يراه إلا المستخدمون المخولون. أما أوامر الشراء والفواتير والتقارير فستعرض الاسم المستعار للمستخدمين المقيّدين، بينما يمكن للإدارة رؤية الاسمين وتعديلهـما. | المرحلة 1 | تطوير | 1
MD-06 | عام | يجب استيراد كتالوج المنتجات بالكامل قبل التشغيل الفعلي، بما يشمل أسماء المنتجات، الأكواد، المتغيرات، الدرجات، وحدات القياس، أسعار البيع حسب الشرائح، أسعار الشراء حسب المورد، وقواعد إعادة الطلب. | سيتم استخدام أداة الاستيراد القياسية في أودو وتزويد العميل بقوالب الاستيراد. ويتحمل العميل مسؤولية تنظيف البيانات وتعبئتها. كما تُستورد أسعار الموردين لكل مورد، وتُضبط جداول تحويل الوحدات يدويًا بعد اكتمال تطوير MD-01. | المرحلة 1 | قياسي
MD-07 | عام | يجب ترحيل جميع العملاء والموردين الحاليين إلى أودو قبل التشغيل. بيانات العملاء تتضمن الاسم ووسائل الاتصال وشريحة السعر والحد الائتماني وشروط الدفع وتصنيف نقدي/آجل، أما الموردون فتتضمن بياناتهم الاسم المستعار والاسم الحقيقي وشروط الدفع والعملة. | يتم استيراد العملاء والموردين باستخدام الاستيراد القياسي مع إعداد ملفات مستقلة لكل منهما، وإدراج الحد الائتماني وشروط الدفع والشرائح السعرية ضمن ملف العملاء. ويكون الاسم المستعار هو الاسم الافتراضي للمورد، بينما يُملأ الاسم الحقيقي في الحقل المخصص بعد تفعيل تطوير MD-05. | المرحلة 1 | قياسي
2. المبيعات وإدارة علاقات العملاء
SAL-01 | المبيعات | الشركة تعمل بهيكل مبيعات بين ثلاث شركات: A وB كمورّدتين، وC كواجهة البيع التجارية للعملاء. العميل يتعامل مع C في العروض والفواتير والمراسلات، لكن المنتجات قد تُسحب من A أو B بحسب التوفر، وفي النهاية تصدر الوثائق القانونية باسم الشركة التي تحمل التسجيل الضريبي والمخزون، مع بقاء هوية C أمام العميل. | المطلوب تطوير نموذج مخصص للمبيعات بين الشركات. يقوم المستخدم بإدخال الطلب عبر نموذج جديد ثم يحدد من أي شركة سيتم أخذ كل منتج، وبعد ذلك ينشئ النظام أوامر البيع والتسليم والفواتير الفعلية في A أو B عند الحاجة، مع أزرار ذكية لربط السجلات والوثائق، ومنطق مشابه للمدفوعات، وتقارير مطبوعة مخصصة، وآلية ربط بين سجلات الشركات المختلفة. | المرحلة 1 | تطوير | 18
SAL-02 | المبيعات | العملاء مقسمون إلى خمس شرائح سعرية: مفرد، نصف جملة، جملة، VIP، وشريك. ويجب تعيين قائمة الأسعار المناسبة لكل عميل وتطبيقها تلقائيًا على أوامر البيع ونقطة البيع. | يتم تفعيل قوائم الأسعار في المبيعات وإنشاء القوائم الخمس، وضبط قواعد التسعير لكل فئة منتجات، ثم ربط كل عميل بالقائمة المناسبة ليتم تطبيقها تلقائيًا في أوامر البيع ونقطة البيع. | المرحلة 1 | قياسي
SAL-03 | المبيعات | يُصنف العملاء إلى نقدي وآجل. العميل النقدي لا يحصل على ائتمان ويجب حظر التسليم حتى تُدفع الفاتورة بالكامل أو يوافق المدير على الإفراج. كما يكون التصنيف الافتراضي لأي عميل جديد هو نقدي. | سيتم إضافة حقل منطقي باسم عميل نقدي في بطاقة العميل ومفعّل افتراضيًا. وعند تأكيد أمر بيع لعميل نقدي يُحظر التسليم تلقائيًا، ولا يُفرج عنه إلا عند السداد الكامل أو بموافقة مدير مخول، مع إظهار سبب الحظر بوضوح. | المرحلة 1 | تطوير | 1
SAL-04 | المبيعات | يجب أن يرى المستخدم في كل سطر بيع حقلي مرجعية للقراءة فقط: آخر سعر بيع لنفس المنتج لهذا العميل، وآخر سعر بيع لنفس المنتج لأي عميل ضمن نفس الشريحة السعرية، مع تحديثهما عند تغيير العميل أو المنتج. | سيتم إضافة حقلين محسوبين في سطر البيع: آخر سعر لهذا العميل وآخر سعر لهذه الشريحة، على أن يتم جلبهما من أحدث أوامر البيع المؤكدة، وإظهارهما في نموذج السطر والقائمة بشكل واضح وغير قابل للتعديل. | المرحلة 1 | تطوير | 1
SAL-05 | المبيعات | لكل متغير منتج حد أدنى قابل للضبط لسعر البيع حسب وحدة القياس. وإذا أدخل البائع سعرًا أقل من الحد الأدنى، فيجب حظر تأكيد الطلب وتشغيل مسار موافقة. كما يجب أن يتغير الحد الأدنى تلقائيًا عند تبديل الوحدة اعتمادًا على معامل التحويل. | سيتضمن التطوير إضافة حقل الحد الأدنى لسعر البيع على مستوى المتغير، والتحقق من سعر السطر عند الحفظ أو التأكيد. وإذا كان السعر أقل من المسموح يتم المنع وإطلاق موافقة مبيعات، مع إعادة احتساب الحد الأدنى تلقائيًا عند تغيير الوحدة وربطه بتطوير MD-01. | المرحلة 1 | تطوير | 2 | minimum regardless of the discounts/promotions
SAL-06 | المبيعات | يجب أن تكون هناك موافقات مستقلة قبل تنفيذ بعض الحالات، مثل إضافة مواد هدية، وتجاوز الحد الائتماني للعميل، وتجاوز مدة التأخير المسموح بها. | يتم تفعيل موافقات أوامر البيع للحالات المناسبة، مع تكييف التطوير الخاص بالحد الائتماني ومدة التأخير. كما تُضبط مسارات الموافقة لكل شركة مع إرسال إشعارات بريدية تلقائية إلى المدير المختص عند الحاجة. | المرحلة 1 | تطوير | 3 | What is the sequence of approvals?
SAL-07 | المبيعات | يجب السماح بإضافة مواد هدية في أمر البيع، بحيث تُخصم من المخزون عند التسليم لكنها لا تولد إيرادًا، وكل إضافة لهدية يجب أن تمر بموافقة مسبقة. | يتم إنشاء فئة منتجات للهدايا بأسعار صفرية، وإضافة علامة على المنتج بأنه هدية. وإذا تضمن أمر البيع منتجًا معلّمًا كهديّة، يُطلَب اعتماد قبل السماح بتأكيد الأمر. | المرحلة 1 | تطوير
SAL-08 | المبيعات / المحاسبة | لكل عميل آجل يجب تحديد حد ائتماني وأقصى مدة تأخير. وإذا أدّى تأكيد أمر البيع إلى تجاوز أحد الحدين، فيجب حظر الطلب وتحويله لموافقة مدير. | يوجد تطوير سابق يغطي التحكم بالحد الائتماني ومدة التأخير، وسيُراجع ويُكيَّف ليتوافق مع Odoo 19، ثم تُضبط القيم في بطاقة العميل وتُربط بمسار الموافقات. | المرحلة 1 | تطوير
SAL-09 | المبيعات | يجب أن يدعم النظام العروض الترويجية مثل الباقات، والخصومات حسب الكمية، وبرامج اشترِ X واحصل على Y، على مستوى المنتج وقائمة الأسعار. | يتم تفعيل وحدة العروض والخصومات في أودو إنتربرايز، وضبط البرامج الترويجية المختلفة وربطها بقوائم الأسعار المناسبة مع تحديد فترات صلاحية للتفعيل والإيقاف. | المرحلة 1 | قياسي
SAL-10 | المبيعات | يجب إدخال معلومات التوصيل مباشرة في أمر البيع، بما في ذلك عنوان التوصيل ورسوم التوصيل كسطر مستقل. | سيُستخدم حقل عنوان التوصيل القياسي في أمر البيع، وتُنشأ خدمة باسم رسوم التوصيل لتُضاف كسطر يدوي منفصل. | المرحلة 1 | قياسي
SAL-11 | المبيعات / المحاسبة | يجب تحديد السائق على إذن التسليم، مع احتساب نسبة قابلة للضبط من رسوم التوصيل كعمولة تُنسب إلى السائق المعين. | سيتم إضافة نسبة عمولة في بطاقة الموظف، وإضافة علامة على منتج رسوم التوصيل، مع السماح بسطر توصيل واحد فقط في الطلب. وعند إنشاء التسليم يتم تحديد السائق ونسبة العمولة الافتراضية والحساب التحليلي، ثم تُحتسب العمولة من رسوم التوصيل بما يتوافق أيضًا مع منطق SAL-01. | المرحلة 1 | تطوير | 4
SAL-12 | المبيعات | عمولات مندوبي المبيعات الداخليين يجب أن تُحتسب على هامش الربح للفواتير المدفوعة بالكامل فقط، مع استبعاد الفواتير غير المدفوعة بالكامل. كما يجب أن يرى المندوب نسبة تحقيق الهدف فقط دون المبالغ، بينما يرى المدير كامل التفاصيل. | سيتم تعديل منطق العمولة ليعتمد على الهامش لا الإيراد، واستبعاد أي فاتورة غير مسددة بالكامل، ثم إنشاء عرضين للوحة العمولة: عرض للمندوب بالنسبة فقط، وعرض للمدير بكل القيم. كما يُضاف حقل هدف دوري عبر Odoo Studio. | المرحلة 1 | تطوير | 7
SAL-14 | المبيعات | يجب إخفاء تكلفة المنتجات عن مستخدمي المبيعات العاديين، وقصر رؤيتها على المديرين أو الإداريين. | هناك تطوير قائم لإخفاء التكاليف على مستوى الواجهات، وسيُراجع مع إضافة أي حالات خاصة قد تظهر أثناء الاستخدام. | المرحلة 1 | تطوير | 0.25
SAL-15 | إدارة علاقات العملاء | يجب أن يرى كل مندوب فقط العملاء المحتملين والفرص الخاصة به، بينما يحتفظ المدير برؤية كاملة لجميع الفرص. | يتم الاعتماد على صلاحيات CRM القياسية وضبط وصول المندوب إلى فرصه الخاصة فقط، مع إبقاء رؤية المدير شاملة لكل الفريق. | المرحلة 1 | قياسي
SAL-18 | المبيعات | يجب معالجة المرتجعات داخل نفس الشركة التي قامت بالبيع. وخلال مدة قابلة للإعداد - حاليًا 3 أيام - تبقى الفاتورة قابلة للتعديل، ويمكن إعادة الفاتورة والتسليم إلى مسودة للمرتجعات الجزئية. بعد ذلك تُقفل التعديلات ويستلزم الأمر موافقة مدير ومعالجة مرتجع رسمية. | سيتم إضافة إعداد لمدة نافذة المرتجع على مستوى الشركة، مع تمكين مستخدمين محددين من إعادة الفاتورة والتسليم إلى مسودة داخل المدة. وبعد انتهائها تُمنع التعديلات وتتم المرتجعات عبر إشعار دائن ومرتجع مخزني بموافقة مدير، مع مجموعة صلاحيات خاصة ومؤشر يوضح ما إذا كانت النافذة مفتوحة أو مغلقة. | المرحلة 1 | تطوير | 1.5
SAL-20 | المبيعات | بعض المستخدمين المخولين فقط يجب أن يتمكنوا من تأكيد المبيعات حتى عند عدم توفر المخزون، أي السماح بالمخزون السالب وفق صلاحيات محددة. | سيتم إنشاء مجموعة صلاحيات خاصة للمستخدمين المخولين بالسماح بالبيع مع مخزون سالب. | المرحلة 1 | تطوير | 1
SAL-21 | المبيعات / إدارة علاقات العملاء | تحتاج الإدارة إلى تقرير شهري يوضح عدد العملاء الجدد المكتسبين حسب شهر الإنشاء لمتابعة نمو قاعدة العملاء. | يمكن استخدام تقرير جهات الاتصال القياسي مع التجميع حسب تاريخ الإنشاء بالشهر، مع حفظ فلتر مفضل، أو إعداد تقرير أكثر تنسيقًا عبر Studio عند الحاجة. | المرحلة 1 | قياسي
SAL-22 | المبيعات / المحاسبة | تحتاج الإدارة إلى تقرير يوضح الزمن بين تاريخ الفاتورة وتاريخ السداد الكامل لكل فاتورة لتحليل سرعة التحصيل حسب العميل أو المندوب أو الفترة. | سيتم إضافة حقل تاريخ السداد الكامل وحقل محسوب بعدد الأيام بين الفاتورة والسداد، ثم عرضهما في تقرير قائمة قابل للتصفية. | المرحلة 1 | تطوير | 2
SAL-23 | Sales / Inventory | يجب تحديد المواد بطيئة الحركة، أي المنتجات التي لم تحقق حركة بيع مهمة خلال فترة قابلة للضبط، لدعم قرارات التنزيل أو الترويج. | يوجد تطوير سابق لتقرير المواد بطيئة الحركة وسيتم اعتماده والتحقق منه، مع إمكانية ضبط مدة عدم الحركة مثل 30 أو 60 أو 90 يومًا. | المرحلة 1 | تطوير | 0.5
3. نقطة البيع (POS)
POS-01 | نقطة البيع | يجب أن يتمكن الكاشير من اختيار وحدة القياس لكل منتج في نقطة البيع، مع تعديل السعر تلقائيًا وفق معامل التحويل الخاص بالمنتج. | هذا امتداد لتطوير MD-01 داخل واجهة نقطة البيع، بحيث يظهر اختيار الوحدة لكل سطر ويتم إعادة احتساب سعر الوحدة تلقائيًا. | المرحلة 1 | تطوير |  | Dependent on MD-01 development being completed first
POS-02 | نقطة البيع | يجب أن تعرض نقطة البيع آخر سعر بيع للمنتج، سواء لهذا العميل المحدد أو ضمن شريحته السعرية. | سيتم توسيع منطق SAL-04 إلى واجهة نقطة البيع بإضافة حقلي مرجعية للقراءة فقط يتحدثان عند اختيار العميل أو المنتج. | المرحلة 1 | تطوير |  | Consistent with SAL-04 — same development logic extended to POS
POS-03 | نقطة البيع | يجب أن تطبق نقطة البيع تلقائيًا قائمة الأسعار المناسبة للعميل المختار، مثل مفرد أو نصف جملة أو جملة أو VIP أو شريك. | يتم تفعيل قوائم الأسعار في إعدادات نقطة البيع بحيث تُطبق قائمة العميل تلقائيًا عند اختياره، وتُستخدم قائمة المفرد افتراضيًا عند عدم اختيار عميل. | المرحلة 1 | قياسي
POS-04 | نقطة البيع | يجب فرض الحد الأدنى لسعر البيع في نقطة البيع، وإذا حاول الكاشير البيع بسعر أقل فيجب طلب موافقة مدير عبر PIN قبل إكمال العملية. | سيتم توسيع تطوير SAL-05 داخل POS للتحقق من السعر عند التعديل، وإظهار نافذة PIN للمدير إذا كان السعر أقل من الحد الأدنى، مع تسجيل محاولات PIN الفاشلة. | المرحلة 1 | تطوير |  | Manager PIN configuration to be set up in POS Settings > Restrict Price Modifications
POS-05 | نقطة البيع | يجب السماح بإضافة مواد هدية في نقطة البيع، لكن بعد موافقة مدير عبر PIN، على أن تُخصم هذه المواد من المخزون بشكل طبيعي. | سيُوسع منطق SAL-07 إلى نقطة البيع، بحيث يؤدي إضافة منتج من فئة الهدايا إلى طلب PIN مدير قبل اعتماد السطر، مع إنشاء الحركات المخزنية المعتادة عند إغلاق الجلسة. | المرحلة 1 | تطوير |  | Consistent with SAL-07
POS-06 | نقطة البيع | يجب إمكانية إضافة رسوم التوصيل كسطر خدمي داخل معاملة نقطة البيع، مع احتساب نسبة عمولة للسائق كما هو الحال في المبيعات الخلفية. | سيُضاف منتج رسوم التوصيل إلى منتجات نقطة البيع، ثم يُمدد منطق عمولة السائق من المبيعات الخلفية إلى معاملات POS عند إغلاق الجلسة وترحيلها. | المرحلة 1 | ستوديو / تطوير |  | Consistent with SAL-10
POS-07 | نقطة البيع | يجب تقييد بعض إجراءات نقطة البيع مثل الاسترجاع، والإلغاء، وتعديل الكميات بعد التأكيد، وتغيير الأسعار، بحيث لا تُنفذ إلا من مستخدمين مخولين. | سيتم ضبط قيود نقطة البيع القياسية لتشمل PIN المدير أو أدوار المستخدم المناسبة لتغيير الأسعار، والاسترجاع، والإلغاء، والفراغات. | المرحلة 1 | قياسي
POS-08 | نقطة البيع | يجب أن يستطيع الكاشير البحث عن المنتجات في نقطة البيع بواسطة الكود الداخلي SKU أو من خلال الباركود. | سيتم تفعيل الباركود في إعدادات POS، وتعبئة حقول الكود الداخلي والباركود للمنتجات، واستخدام البحث القياسي الذي يدعم الاسم والباركود والكود. | المرحلة 1 | قياسي |  | Barcode hardware (scanner) to be procured by client — confirm device compatibility with Odoo IoT box if required
POS-09 | نقطة البيع | يجب أن تحتوي كل عملية POS على بائع/موظف محدد يتم اختياره من قائمة موظفي الموارد البشرية لأغراض التقارير والعمولات. | سيتم ضبط POS لإظهار شاشة اختيار الموظف في بداية المعاملة أو عند فتح الجلسة، وربط هذا الحقل بتقارير الأداء والعمولة. | المرحلة 1 | قياسي
POS-10 | نقطة البيع | تحتاج الإدارة إلى تقرير عمولات لموظفي نقطة البيع، قابل للتصفية حسب الموظف والفرع والفترة. | سيتم إنشاء تقرير Studio على أوامر POS يعرض الموظف وإجمالي المبيعات وعدد المعاملات ونسبة العمولة وقيمتها مع فلاتر مناسبة. | المرحلة 1 | ستوديو
POS-11 | نقطة البيع | يجب أن تُحدّث معاملات نقطة البيع المخزون والمحاسبة تلقائيًا عند إغلاق الجلسة، مع تكامل كامل مع المخزون والمحاسبة. | سيتم الاعتماد على تكامل أودو القياسي بين POS والمخزون والمحاسبة، مع إعداد اليومية والمخزن الصحيحين لكل شركة أو فرع. | المرحلة 1 | قياسي
4. المشتريات والمخزون
INV-01 | المخزون | الشركة تعمل عبر 8 مخازن في العراق موزعة على الشركات A وB وC، وكل مخزن يُعد مركز تكلفة يجب تتبعه، مع دعم التحويلات الداخلية وإبقاء المخزون منفصلًا حسب الشركة حتى لو كان المنتج نفسه مشتركًا. | سيتم إنشاء 32 مخزنًا في أودو وفق التصميم المذكور وربط كل مخزن بشركته، وإنشاء حسابات تحليلية لكل مخزن/فرع لتتبع الربحية، مع إعداد مسارات التحويل الداخلية بين المخازن. | المرحلة 1 | قياسي
INV-03 | المخزون | تصل المنتجات الخشبية دون تحديد نهائي للدرجات، وتُحدد درجات A وB وC بعد التفريغ والفرز في مستودع مخصص، لذلك يجب أن يدعم النظام عملية إعادة تصنيف من مخزون غير مصنف إلى درجات مصنفة. | سيتم تنفيذ عملية فرز في موقع مخصص بعد الاستلام، مع نافذة لتحديد اللوت والدرجة لكل لوت عبر نموذج فرز جديد. | المرحلة 1 | تطوير | 2
INV-04 | المخزون / المحاسبة | قبل استلام الشحنة يجب تمكين المستخدم من تسجيل تكاليف شحن/وصول تقديرية تؤثر على تكلفة المنتج، ثم بعد الاستلام يُعاد فتح التكلفة التقديرية واعتماد التكلفة الفعلية بعد ورود الفواتير النهائية. | عمليًا يمكن إنشاء Landed Cost عند الاستلام دون اعتماده، ثم تعديل المبالغ بعد الفوترة واعتماده لاحقًا. وسيُضاف تطوير إضافي ليتكامل هذا مع منطق SAL-01 عبر نموذج تمهيدي ينشئ Landed Cost فعليًا. | المرحلة 1 | تطوير | 3
INV-05 | المخزون / المحاسبة | التكلفة الإضافية للوصول تتكون من رسوم كمركية 15% وضريبة استيراد 3% ونقل وتكاليف أخرى مثل التحميل والميناء والتوصيل والمصاريف المتنوعة، ويجب تتبع كل نوع على حساب مصروف مستقل، مع إدخال 15% و3% يدويًا دون احتساب آلي. | سيتم إعداد بنية التكاليف الإضافية في أودو بحيث يُسجل كل نوع تكلفة بشكل منفصل ويرتبط بحساب مصروف خاص به، وتُدخل نسبتا 15% و3% يدويًا كما هو مطلوب. | المرحلة 1 | قياسي
INV-06 | المخزون / اللوجستيات | يجب تتبع كل شحنة استيراد من خلال رقم بوليصة الشحن BL ورقم الحاوية والوزن والإجمالي الحجمي CBM وحالة الميناء ومرحلة الشحنة من الطلب إلى التسليم، مع إمكانية استخراج تقارير من سجلات الشحن. | سيتم إضافة الحقول المطلوبة على نموذج الاستلام مثل BL والحاوية والوزن وCBM وحالة الميناء ومرحلة الشحنة عبر Studio/تطوير، مع إنشاء تقرير مرتبط بها. | المرحلة 1 | تطوير | 2
INV-07 | المشتريات | يجب أن يدعم المنتج الواحد عدة موردين مع أسعار ومهل توريد وعملات مختلفة، وأن يقترح النظام المورد الأنسب عند إنشاء أمر الشراء. | يتم تفعيل إعداد تعدد الموردين على المنتج وإدخال قائمة الموردين بأسعارهم وكمياتهم الدنيا ومهلهم وعملاتهم، ثم يستفيد أودو من ذلك لاقتراح المورد المناسب تلقائيًا. | المرحلة 1 | قياسي
INV-08 | المشتريات | تحتاج الإدارة إلى متابعة أداء الموردين من حيث اتجاهات الأسعار، والتأخير عن المهل المتفق عليها، ودقة التسليم مقارنةً بالكميات المطلوبة. | سيتم استخدام تقارير الشراء والاستلام القياسية لتحليل أداء الموردين، ويمكن بناء لوحة إضافية عبر Studio أو Spreadsheet لعرض متوسط التأخير ودقة التسليم وتغير الأسعار. | المرحلة 1 | قياسي
INV-10 | المشتريات / المخزون | تحتاج الإدارة إلى رؤية الطلب الشهري واليومي على المنتجات لدعم قرارات الشراء وإعادة التوريد. | سيُستخدم تقرير التنبؤ بالمخزون لعرض الطلب اليومي ضمن أفق 30 يومًا، مع إعداد Pivot على الحركات الصادرة لإظهار الاستهلاك الشهري لكل منتج. | المرحلة 1 | قياسي
INV-11 | المخزون | أثناء الجرد الفعلي يجب أن يعرض النظام القيمة المالية لفروقات الجرد، محسوبة من فرق الكمية مضروبًا في سعر التكلفة. | سيتم إضافة حقل محسوب باسم قيمة الفرق في شاشة الجرد ليعرض أثر الفرق المالي، كما يُدرج في تقرير تسويات المخزون. | المرحلة 2 | تطوير | 1
INV-12 | المخزون | يجب الحفاظ على تتبع كامل للمخزون من الاستلام وحتى موقع التخزين، مع إمكانية الرجوع إلى اللوت أو السيريال وتاريخ الحركات وأمر الشراء الأصلي والشحنة المصدرية. | سيتم تفعيل تتبع اللوتات/السيريال حسب الفئات، وضبط المواقع والمخازن الفرعية، والاعتماد على تقارير التتبع القياسية في أودو. | المرحلة 1 | قياسي
INV-13 | المخزون | عمليات المستودع مثل الاستلام والتحويلات الداخلية والالتقاط والتسليم يجب أن تدعم الباركود، وكذلك تطبيق أودو على الجوال. | سيتم تفعيل وحدة الباركود وضبطها لعمليات المخزن المختلفة، مع تهيئة التطبيق الجوال لموظفي المستودع لاستخدام المسح. | المرحلة 1 | قياسي
5. المحاسبة والمالية
ACC-01 | المحاسبة | يجب تطبيق الحد الائتماني ومدة التأخير على جميع قنوات البيع مع حظر البيع عند التجاوز حتى الحصول على موافقة. | هذا المطلب تمت معالجته ضمن SAL-08. | المرحلة 1 | تطوير | 0
ACC-02 | المحاسبة | يجب إصدار كشوفات حساب العملاء وتذكيرات الدفع آليًا وفق فترات قابلة للضبط، مع تصاعد في التذكير حسب عمر الاستحقاق. | سيتم تفعيل وحدة المتابعات account_followup وضبط مستويات تذكير مثل 7 و15 و30 يومًا، مع تخصيص قوالب البريد وتشغيل الإرسال الآلي يوميًا. | المرحلة 1 | قياسي
ACC-03 | المحاسبة / المخزون | كل تكاليف الوصول يجب أن تُوزع على المخزون وتنعكس في التكلفة الفعلية للمواد بحيث يظهر COGS الحقيقي. | سيتم استخدام ميزة Landed Costs القياسية وتحديد أسلوب التوزيع المناسب حسب النوع: كمية أو وزن أو حجم أو تكلفة حالية، مع اعتماد التقييم بطريقة AVCO للمنتجات الخشبية. | المرحلة 1 | قياسي
ACC-04 | المحاسبة | يجب أن تنتج عمولات السائقين والبائعين قيودًا محاسبية قابلة للتتبع، بحيث تكون عمولة السائق من أجور التوصيل وعمولة البائع من هوامش الفواتير المسددة. | هذا المطلب تمت تغطيته ضمن SAL-11 وSAL-12. | المرحلة 1 | تطوير | 0
ACC-05 | المحاسبة | يجب أن يدعم النظام تعدد العملات في المشتريات والمدفوعات والتقارير، مع إمكانية تحديد سعر صرف على مستوى الدفع وتجاوزه يدويًا عند الحاجة. | سيتم تفعيل تعدد العملات في المحاسبة واستخدام التطوير القائم لسعر الصرف على الفواتير والمدفوعات والقيود، مع إضافة منطق لأرباح/خسائر فروقات العملة حسب سياسة العمل. | المرحلة 1 | تطوير | 2
ACC-06 | المحاسبة | تحتاج الإدارة إلى تقارير الذمم المدينة والأعمار الزمنية للأرصدة حسب العميل والفترة والفرع، مع إمكانية التصدير PDF وExcel. | سيُستخدم تقرير Aged Receivable القياسي في أودو مع الفلاتر المناسبة حسب الشركة أو الفرع، والتصدير متاح افتراضيًا. | المرحلة 1 | قياسي
ACC-07 | المحاسبة | يجب أن يكون الإيراد قابلاً للتقسيم والتحليل حسب درجة الخشب وفئة المنتج والفرع/المخزن والشركة ومندوب المبيعات. | سيتم استخدام الحسابات التحليلية والوسوم لتقسيم الإيراد، مع بناء تقارير عبر الربحية أو الجداول المحورية أو Odoo Spreadsheet حسب الحاجة. | المرحلة 1 | قياسي
ACC-08 | المحاسبة | هناك حاجة لحساب عبء/رسم معين بناءً على الوزن بدلًا من القيمة لبعض المنتجات. | لن يتم تعديل منطق الضرائب القياسي في أودو. بدلًا من ذلك سيُضاف خيار لإنشاء سطر مستقل باسم رسم استيراد أو واجب وزني يُحتسب من الوزن الكلي × تعرفة ثابتة، دون تطبيق ضريبة عليه. | المرحلة 1 | تطوير | 1.25 | it will be a line item instead of tax, as tweaking the tax logic in thhe system is a huge process
ACC-09 | المحاسبة | تقرير مدة التحصيل بين تاريخ الفاتورة وتاريخ السداد الكامل مطلوب على مستوى المحاسبة أيضًا. | هذا المطلب تمت تغطيته ضمن SAL-22. | المرحلة 1 | تطوير | 0
ACC-10 | المحاسبة / المخزون | تحتاج الإدارة إلى تقرير يوضح التكلفة التقريبية الحالية لكل منتج بعد تضمين جميع مكونات التكاليف الإضافية والبدائل. | التقرير القياسي في Odoo 19 لا يعرض ذلك بالشكل المطلوب لكل منتج، وقد يتطلب الأمر تقرير SQL مخصصًا، لكن الملاحظة التقنية تشير إلى أن العائد من هذا التطوير منخفض وقد يكون من الأفضل إسقاطه. | المرحلة 1 | تطوير | 3.75 | This is huge and the ROI for it is not worth it. shoiuld be dropped
ACC-11 | المحاسبة | يجب أن تكون لكل شركة قوائم مالية مستقلة، مع إتاحة تقارير مجمعة على مستوى المجموعة للإدارة. | سيتم إعداد دليل حسابات مستقل لكل شركة، واستخدام التقارير المالية القياسية على مستوى الشركة، مع تفعيل وحدة الدمج Consolidation إن كانت متاحة لعرض النتائج المجمعة. | المرحلة 1 | قياسي
ACC-12 | المحاسبة | يجب إدخال الأرصدة الافتتاحية قبل التشغيل، بما فيها أرصدة العملاء والموردين والبنوك وتقييم المخزون لكل شركة. | تُدخل الأرصدة الافتتاحية عبر قيود يومية في المحاسبة، وتُستورد الفواتير المفتوحة باستخدام الاستيراد القياسي، كما تُدخل أرصدة البنوك وتسويات المخزون الافتتاحية بعد تجهيز الكتالوج والمخازن. | المرحلة 1 | قياسي
6. الموارد البشرية
HR-01 | الموارد البشرية | مطلوب قاعدة بيانات شاملة للموظفين تشمل البيانات الشخصية والعملية، العقود، المسميات، الهيكل الإداري، وأرشفة المستندات مثل الهويات والشهادات. | سيتم إعداد وحدة الموظفين والهيكل التنظيمي، وإنشاء سجلات لجميع الموظفين واستيرادها من ملفات جاهزة، مع رفع المستندات إلى تبويب الوثائق في بطاقة الموظف. | المرحلة 1 | قياسي
HR-02 | الموارد البشرية / الحضور | يجب ربط أجهزة البصمة ZKTeco مع أودو لتسجيل الحضور والانصراف آليًا مع كشف الحالات غير الطبيعية. | سيتم دمج أجهزة ZKTeco مع وحدة الحضور في أودو عبر موصل مناسب وضبط الاتصال والمزامنة الدورية، إلى جانب إعداد جداول الدوام والتنبيهات للحالات الناقصة. | المرحلة 1 | تطوير | 0.5
HR-03 | الموارد البشرية | إدارة أنواع الإجازات المختلفة مثل السنوية والمرضية وغير المدفوعة، مع تقديم الطلبات عبر الخدمة الذاتية ومسارات اعتماد حسب الهيكل الإداري. | سيتم إعداد وحدة الإجازات مع الأنواع الثلاثة وقواعد الاستحقاق لكل نوع، وتفعيل بوابة الخدمة الذاتية ومسارات الموافقات حسب المدير المباشر أو الموارد البشرية. | المرحلة 1 | قياسي
HR-04 | الموارد البشرية | يجب إدارة العقود بما يشمل تواريخ البداية والنهاية والراتب ونوع العقد مع تنبيهات تلقائية قبل انتهاء العقود. | سيتم إعداد وحدة العقود وإنشاء سجل لكل موظف يتضمن تفاصيل العقد، مع إجراء آلي ينبه الموارد البشرية قبل 30 أو 60 يومًا من الانتهاء. | المرحلة 1 | قياسي
HR-05 | الموارد البشرية / المحاسبة | يجب معالجة الرواتب بناءً على الحضور والإجازات وشروط العقود، مع دعم المعالجة الجماعية وقسائم الرواتب والتكامل مع المحاسبة. | سيتم إعداد وحدة الرواتب بالقواعد والاستقطاعات والبدلات المناسبة وربط جداول العمل بالحضور، مع توليد قيود محاسبية تلقائية عند اعتماد مسيرات الرواتب. | المرحلة 1 | قياسي
HR-06 | الموارد البشرية | يجب أن يعكس النظام الهيكل الإداري للأقسام، وأن تمر الموافقات المرتبطة بالموارد البشرية وفق هذا الهيكل. | سيتم إنشاء الأقسام والمديرين في وحدة الموظفين وضبط مسارات الموافقات للإجازات والمصاريف والتغييرات الإدارية حسب التسلسل الإداري. | المرحلة 1 | قياسي
HR-07 | الموارد البشرية / عام | يجب تقييد كل مستخدم بالوحدات والوظائف المرتبطة بعمله فقط، مع حصر الإجراءات الحساسة مثل تجاوز الأسعار أو موافقات الائتمان أو إظهار أسماء الموردين الحقيقية على أدوار محددة. | سيتم إعداد مصفوفة صلاحيات مستخدمين وتوثيقها، وربط كل مستخدم بالأدوار القياسية أو المخصصة المناسبة مثل مدير المرتجعات أو معتمد الائتمان قبل الإطلاق. | المرحلة 1 | قياسي
HR-08 | الموارد البشرية | مطلوب تدريب المستخدمين على وحدة الموارد البشرية، بما يشمل سجلات الموظفين والإجازات والحضور والعقود والرواتب. | سيتم تنفيذ جلستي تدريب مدة كل منهما ساعتان، مع تسجيل الجلسات وتوفير دليل استخدام للمستخدمين. | المرحلة 1 | قياسي
7. اللوجستيات والأسطول
LOG-01 | اللوجستيات / المخزون | كل إذن تسليم يجب أن يدعم تعيين سائق محدد، مع ربط ذلك بمنطق عمولة رسوم التوصيل. | هذا المطلب تمت تغطيته ضمن SAL-10/SAL-11. | المرحلة 1 | تطوير | 0
LOG-02 | اللوجستيات / المخزون | يجب تتبع دورة حياة الشحنة من الطلب إلى الشحن ثم الوصول للميناء والكمارك والإفراج والتسليم، مع حفظ BL والحاوية والوزن وCBM والحالة وموعد الوصول المتوقع. | هذا المطلب مرتبط بتطوير تتبع الشحنات والحاويات المذكور في INV-06 ويُنفذ ضمن نفس المنطق. | المرحلة 1 | تطوير | 0
LOG-03 | اللوجستيات / المخزون | تكاليف خدمات الكرين والشاحنات المستخدمة في التنزيل أو التوصيل يجب تسجيلها وربطها بالشحنة أو العملية المخزنية المعنية. | سيتم تعريف هذه الخدمات كمنتجات خدمية وإدراجها في فواتير الموردين وربطها بالحساب التحليلي الخاص بالشحنة أو العملية من أجل تتبع التكلفة. | المرحلة 1 | قياسي
LOG-04 | اللوجستيات | يجب إدارة مركبات التوصيل المملوكة للشركة داخل أودو، بما يشمل بيانات المركبات والسائقين والخدمات والتكاليف. | سيتم تفعيل وحدة الأسطول وإدخال سجلات المركبات مع رقم اللوحة والتأمين والسائق المعين وسجلات الخدمة والوقود. | المرحلة 1 | قياسي
8. التقارير ولوحات المعلومات
RPT-01 | التقارير | تحتاج الإدارة إلى لوحة أداء فورية للمندوبين تعرض الهدف مقابل المنجز، والتحصيلات، والعمولة، وأفضل المنتجات، مع إخفاء القيم المالية عن المندوبين وإظهارها للمديرين. | يتطلب ذلك تكييف اللوحة مع منطق العمولات الجديد وهيكل الشركات المتعددة، بينما كثير من الحقول الأساسية موجودة أصلًا في النظام. | المرحلة 1 | تطوير | 3.5
RPT-02 | التقارير | يجب توفير تحليلات للمبيعات والمخزون حسب المنتج ودرجة الخشب والأبعاد لتحديد أكثر الخطوط ربحية وأقلها. | يمكن استخدام تقارير التحليل القياسية في المبيعات والمخزون مع التجميع حسب الفئة والدرجة والأبعاد، وبناء تقرير ربحية إضافي عبر Spreadsheet إذا لزم الأمر. | المرحلة 1 | قياسي
RPT-03 | التقارير | تحتاج الإدارة إلى تقرير أعمار مخزون الأخشاب يوضح مدة بقاء كل مادة في المخزون ضمن شرائح عمرية. | سيتطلب ذلك تطوير تقرير أعمار على مستوى اللوت لأن الدرجة مرتبطة باللوت. | المرحلة 1 | تطوير | 1
RPT-04 | التقارير / المخزون | يجب أن يعرض تقرير تقييم المخزون القيمة الحالية للمخزون حسب المنتج والمخزن والشركة بعد تضمين التكاليف الإضافية. | سيتم الاعتماد على تقرير تقييم المخزون القياسي في أودو مع حفظ فلاتر سريعة لكل شركة أو مخزن. | المرحلة 1 | قياسي
RPT-05 | التقارير / اللوجستيات | تحتاج الإدارة إلى تقرير أداء التوصيل لقياس الالتزام بالوقت ومتوسط زمن التسليم مع تحليل حسب السائق والفرع. | سيتم إضافة بعض الحقول اللازمة ثم استخدام عرض قائمة أو تقرير بسيط مبني على عمليات التسليم والاستلام. | المرحلة 1 | تطوير | 0.5
RPT-06 | التقارير / المحاسبة | يجب توفير لوحة لحظية للذمم والائتمان تعرض إجمالي المستحقات والعملاء المتجاوزين للحدود والعملاء المتأخرين وتحليل الأعمار على مستوى الفروع. | سيُستخدم تقرير الذمم المدينة القياسي كأساس، مع بناء لوحة إدارة عبر Studio تتضمن المؤشرات المذكورة وتدعم التصفية حسب الشركة والفرع. | المرحلة 1 | Standard / Studio
RPT-07 | التقارير | يجب أن تدعم جميع التقارير واللوحات التصدير إلى Excel وPDF، مع توفير Odoo Spreadsheet للتقارير الديناميكية المخصصة. | أزرار التصدير متاحة قياسيًا في معظم تقارير أودو، وسيتم تفعيل Odoo Spreadsheet وبناء قوالب جاهزة للتقارير المهمة للإدارة والمالية. | المرحلة 1 | قياسي
9. النظام والتحكم بالوصول

## Original English
Nobel Woods Trading — Gap Analysis: Business Requirements & Solutions
Odoo 19 Enterprise ¦ Iraq ¦ 3 Companies ¦ 18 Users
Ref | Scope | Business Need | Solution | Phasing | Type |  | Technical Comments
0. Company & General Overview
GEN-01 | General | Nobel Woods Trading is a specialised wood trading and processing company operating across Iraq. The business imports multiple grades of timber from various international origins, manages complex supplier relationships, and distributes products across wholesale, retail, and project-based customers. The company also operates a wood-processing division involving machinery-based cutting, shaping, and finishing operations. Key project parameters: • 3 legal companies • 25 employees / 18 system users • Legacy system: Local (non-Odoo) • Hosting: Odoo.sh • Languages: Arabic & English • Country: Iraq | Configuration: Multi-company setup with 3 companies configured in Odoo. Each company to have its own chart of accounts, currency settings, and access rights. Odoo.sh hosting environment to be provisioned with staging and production branches. Configuration: Arabic and English languages to be installed and activated. Document layouts (invoices, POs, delivery orders) to be configured with bilingual output per company. | Phase 1 | Standard
GEN-02 | General | The system must support 3 legal entities: • Company A — Product-supplying entity (holds stock, registered for tax). • Company B — Product-supplying entity (holds stock, registered for tax). • Company C — Main selling entity; commercial face to all customers. Does not hold stock in most cases. Requirements: company-specific access rights, secure data separation, optional shared product catalogue, per-company accounting, optional inter-company rules, and user-based visibility restrictions. | Configuration: Each company to be created as a separate entity in Odoo Settings > Companies. Role-based access control to be configured so users only see the company/companies relevant to their role. Shared product catalogue to be enabled via multi-company product sharing settings. Configuration: Inter-company transaction rules to be reviewed and configured based on agreed workflow between Company A, B, and C. | Phase 1 | Standard
1. Master Data & Product Configuration
MD-01 | Inventory / Sales | Wood products are sold, purchased, and stocked in multiple units of measure including Meters, Bundles, and Cubic Feet. Each product has its own conversion factor between UoMs, which must affect the sales price, cost, and stock quantity accordingly. The secondary UoM must be visible on purchase orders. Users must be able to view inventory stock reports in any configured UoM. | Custom Development: Standard Odoo UoM supports a single global conversion factor per UoM category. Nobel Woods requires product-specific conversion factors where the same UoM (e.g. Bundle) has a different conversion value per product. Development to: - Add a product-level UoM conversion table on the product template - Set Uom and its related unit price - Display secondary UoM and converted quantity on purchase order lines - Extend inventory stock reports to support multi-UoM viewing | Phase 1 | Development | 4
MD-02 | Inventory | Each wood product is classified into three quality grades: Grade A, Grade B, and Grade C. All grades share the same purchase cost but carry different sales prices. The actual grade quantities of a shipment are unknown at time of purchase and are only determined after physical unpacking at a designated grading warehouse. | Development: We will use lots to track the grades - New model to set grade and its multiplier - Grade will be manually set per lot on receiving the product - On selling, once the grade is set (lot), we add the multiplier to the price since we have another dev for UOM | Phase 1 | Development | 2
MD-03 | Inventory / Sales | Wood products have multiple dimension variants (length, thickness, width) and colour variants defined under the same product template | Configuration: Product variants to be enabled in Odoo Settings. Variant attributes (Length, Thickness, Width, Colour) to be created under Inventory > Configuration > Attributes. Each product template to have the relevant attributes assigned, generating the required variant combinations. | Phase 1 | Standard
MD-04 | Inventory / Accounting | The average cost must be calculated at the product template level by considering all variants under that template, weighted by the quantity on hand of each individual variant. Standard Odoo calculates AVCO per individual variant. (only view not overriding) | Custom Development: New field on product - Sum cost / number of variants | Phase 1 | Development | 0.25
MD-05 | Procurement | Each vendor must have two names: an Alias Name visible to all users on purchase orders and related documents, and an Actual Vendor Name visible only to users with specific administrator-level access. This is required to protect the confidentiality of vendor relationships from general staff. | Custom Development: A development is required to: - Add an 'Actual Vendor Name' field on the vendor/contact record (in addition to the standard Name field which becomes the Alias) - Apply record-level security rules so that the Actual Vendor Name field is only visible to users with the designated access group - Ensure all POs, bills, and reports display only the Alias Name for restricted users - Administrator-level users can see and edit both names | Phase 1 | Development | 1
MD-06 | General | Master Data: Product Catalogue All wood products, variants, grades, and UoMs must be imported into Odoo prior to go-live. This includes product names, codes (SKUs), variant attributes, sales prices per pricelist tier, purchase prices per supplier, and reorder rules. | Master Data: Product catalogue to be imported using the standard Odoo import utility (Settings > Technical > Import). Odoo import templates to be provided to the client. Client is responsible for populating and cleansing the data before import. Master Data: Supplier price lists to be imported against each vendor record. UoM conversion tables to be configured manually per product after the custom UoM development (MD-01) is deployed. | Phase 1 | Standard
MD-07 | General | Master Data: Customer & Vendor Records All existing customers and vendors must be migrated into Odoo prior to go-live. Customer records must include: name, contact details, assigned pricelist tier, credit limit, payment terms, and cash/credit classification. Vendor records must include: alias name, actual name, payment terms, and currency. | Master Data: Customer and vendor records to be imported using standard Odoo import utility. Separate import sheets to be prepared for customers and vendors. Credit limits, payment terms, and pricelist assignments to be included in the customer import template. Master Data: Vendor alias names to be the default Name field. Actual vendor names to be populated in the custom field (see MD-05) after development is deployed. | Phase 1 | Standard
2. Sales & CRM
SAL-01 | Sales | Inter-Company Sales Structure: The company operates through a multi-company commercial structure consisting of three entities: - Company A: Product supplying entity - Company B: Product supplying entity - Company C: Main selling entity responsible for customer transactions Agreed Process: 1. All customer interactions, quotations, and invoicing are handled by Company C, which acts as the commercial interface with the customer. 2. Products sold to customers may originate from Company A or Company B, depending on product availability and sourcing requirements. In rare cases, Company C may also source and deliver products directly. 3. Customers place their orders with the sales team under Company C, which represents the brand known to the market. 4. The sales team handles all communication, quotations, and order confirmations using Company C details, as this is the identity customers recognize. 5. Once the order is confirmed, the system determines which entity (Company A or Company B) will supply the requested products based on rules and stock levels 6. Since Company C does not hold stock, all products are sourced from either Company A or Company B and rarely (local sales) Company C 7. Internally, the order is then recorded under the supplying company (A or B) as the entity responsible for the transaction. 8. The customer information remains the same end customer who originally placed the order with Company C. 9. The supplying company prepares the order and arranges the delivery to the customer 10. For legal and tax purposes, the official sales order and invoice are issued under Company A or Company B, since these entities hold valid TRN registrations. 11. At the same time, the documents provided to the customer (sales order, delivery documents, and invoice) must carry the Company C name and branding, as this is the commercial identity used in the market. | Custom Development: A custom inter-company sales model is required. The development must: - Create a new model to replicate sale.order - Use this model to create actual sale order in company A and B NOT C - If they sell from C, they use normal sale order - Once they select the products and confirm, they should be able to see a wizard where they choose which company each product should be taken from (provided its there in BOTH companies) - After this another button should create actual deliveries -> Another one to confirm (returns will have to be done manually) - Smart button to show actual eliveries and invoices and SOs - Need similar logic for payments too - New reports to be printing from this new model -> Sales quotation, proforma, actual invoice - If they have routes -> this wont work - Make sure there is a way to link the two separate records on two companies (maybe a new id field or same sequence number). This will be needed later. Every development below has to work with this model AND sale order | Phase 1 | Development | 18
SAL-02 | Sales | Customer Segmentation (Pricing Tiers): Customers are segmented into five pricing tiers, each with a dedicated pricelist: 1. Retail 2. Half Wholesale 3. Wholesale 4. VIP 5. Partner The correct pricelist is assigned to each customer and applied automatically on all sales orders and POS transactions. | Configuration: Pricelists to be enabled in Sales > Settings. Five pricelists to be created: - Retail (base price) - Half Wholesale - Wholesale - VIP - Partner Configuration: Each pricelist to be configured with the agreed pricing rules per product category. Pricelist to be assigned to each customer on the contact record and auto-applied on sales orders and POS. | Phase 1 | Standard
SAL-03 | Sales | Customer Segmentation (Payment Type): Customers are classified as either Cash Customers or Credit Customers. Cash Customers receive no credit, delivery must be blocked until the invoice is fully paid or a manager approves release. Cash Customer is the default classification for all new customers. Credit Customers are subject to credit limit and overdue duration rules (see SAL-11). | Custom Development: A development is required to: - Add a 'Cash Customer' boolean field on the contact record, checked by default for all new customers - When a sales order is confirmed for a Cash Customer, automatically block the related delivery order - The delivery order can only be released when: (a) the linked invoice is fully paid, OR (b) a manager with the appropriate access right manually approves the release - A clear visual indicator on the delivery order to show it is blocked and the reason | Phase 1 | Development | 1
SAL-04 | Sales | Last Selling Price Display: On every new sales order line, users must be able to view two read-only reference price fields: 1. The last price at which that specific product was sold to this specific customer. 2. The last price at which that product was sold to any customer within the same pricing tier (pricelist segment). Both fields must update dynamically when the customer or product is changed. | Custom Development: Two computed read-only fields to be added on the sales order line (sale.order.line): It will be UNIT PRICE - 'Last Price (This Customer)': queries the most recent confirmed sales order line for the same product and same customer - 'Last Price (This Segment)': queries the most recent confirmed sales order line for the same product sold to any customer on the same pricelist Both fields to be displayed on the sales order line form and list view. Fields must be non-editable and clearly labelled. | Phase 1 | Development | 1
SAL-05 | Sales | Minimum Sales Price: Each product variant must have a configurable minimum sales price per UoM. If a salesperson enters a price below this threshold, the system must block order confirmation and trigger an approval workflow. The minimum price must adjust dynamically when the UoM is changed on the order line, using the same UoM conversion factor. Add an approval for selling below a minimum price. Should be linked to - MD-01 | Custom Development: Development required to: - Add a 'Minimum Sales Price' field at the product variant level (product.product) - Validate the sales order line unit price against the minimum price on every save/confirmation attempt - If price is below minimum: block confirmation and trigger the standard Odoo sales approval workflow (or custom approval if not sufficient) - Minimum price to dynamically recalculate when UoM is changed on the line, using the conversion factor from MD-01 1 day if its only unit price or discount. 2 days if it needs to cover both. | Phase 1 | Development | 2 | minimum regardless of the discounts/promotions
SAL-06 | Sales | Approval Workflows: The following scenarios must each trigger a dedicated approval workflow before the sales order or action can proceed: 1. Adding gift items to a sales order 2. Exceeding a customer's credit limit 3. Exceeding a customer's overdue duration threshold | Configuration: Sales approval workflow to be enabled (Sales > Settings > Order Approval). To be configured for scenarios 1 and 2 where applicable. Custom Development: For credit limit (scenario 3) and overdue duration (scenario 4), existing development to be reused/adapted. Approval routing to be configured per company with the designated approver role. Approval email notifications to be configured using automated actions so the relevant manager receives an alert with order details when approval is triggered. | Phase 1 | Development | 3 | What is the sequence of approvals?
SAL-07 | Sales | Gift Items: Salespersons must be able to add gift items to a sales order. Gift items deduct from inventory upon delivery but generate no revenue. Adding any gift item must trigger an approval workflow before the order can be confirmed. | Configuration: A product category 'Gift Items' to be created. Products in this category to have a sales price of zero and be flagged as requiring approval when added. Custom Development: - On product add a new checkbox "is gift" - On sale order, if there is a product with this check box true, trigger an approval, only once this approved can the sale order be confirmed | Phase 1 | Development
SAL-08 | Sales / Accounting | Credit Limit & Overdue Duration Control: Each credit customer must have a defined credit limit (maximum outstanding receivable balance) and an overdue duration threshold (maximum days a payment can remain overdue). When a sales order confirmation would breach either threshold, the order must be blocked and routed to a manager for approval. | Existing Development: Credit limit and overdue duration enforcement is covered by an existing Odoo development. This development to be reviewed for compatibility with Odoo 19 and adapted if necessary. Configuration: Credit limit and overdue duration values to be set per customer on the contact record. Approval workflow to be aligned with SAL-06. | Phase 1 | Development
SAL-09 | Sales | Promotions & Bundles: The system must support promotional pricing including bundle pricing, quantity-based discounts, and Buy X Get Y promotions. These must be configurable per pricelist and per product. | Configuration: Promotions & Discounts module to be activated (part of Odoo Enterprise Sales). Promotional programs to be configured for: - Quantity-based discounts (tiered pricing per product) - Bundle pricing (fixed price for a set of products) - Buy X Get Y (free product after quantity threshold) Configuration: All promotion rules to be linked to the relevant pricelists and activated/deactivated with a validity date range. | Phase 1 | Standard
SAL-10 | Sales | Delivery Information on Sales Order: Delivery details including the delivery address and delivery fees must be capturable directly on the sales order. Delivery fees must appear as a separate line item. | Configuration: Delivery address to use the standard Odoo 'Deliver to' field on the sales order, linked to the customer's delivery addresses. Configuration: Delivery fee to be configured as a service product (e.g. 'Delivery Fee') and added as a manual line item on the sales order. | Phase 1 | Standard
SAL-11 | Sales / Accounting | Delivery Fees & Driver Commission: On the delivery note the user should define the driver assigned. A configurable percentage of each delivery fee charged to the customer must be automatically allocated as commission to the assigned driver. | A commission percentage field to be added on the HR Employee record This has to work with SAL-01 Custom Development: - Add new checkbox on product "is delivery" - On sale order allow only one is delivery product (this should also apply to new model from SAL-01) - Once a delivery is created, they set the responsible employee, commission % (default from hr), analytic account (default from hr), - We can get the delivery fee from the sale order - Make sure this works with edge cases, with the new model and standard sale order | Phase 1 | Development | 4
SAL-12 | Sales | Salesperson Commission (Internal Users): Commissions for salespeople (Odoo users) must be calculated based on the margin of fully paid invoices only. Partially paid invoices must be excluded. Salespeople may only view their commission as a percentage of target achieved monetary amounts must be hidden from salesperson-level users. Managers see full details including monetary targets, collections, and percentage achieved. | Custom Development: Development required to: - Modify commission calculation to use invoice margin (revenue minus product cost) rather than revenue - Exclude invoices that are not fully paid (payment_state != 'paid') from commission calculation - Create two views of the commission dashboard: Salesperson view (% of target only, no monetary values) and Manager view (full amounts, all salespeople) Studio: Target amount field to be added per salesperson per period using Odoo Studio on the Employee or Sales Team record. | Phase 1 | Development | 7
SAL-14 | Sales | Sales Cost Visibility: Product cost fields must be hidden from salesperson-level users. Only users with manager or administrator access should be able to view product costs on sales orders and related documents. | Existing dev: - hides the costs on the view level to not interfere with any business logic. so there might be niche cases where the cost shows so I included some buffer in case you find some of these cases so they can be added. | Phase 1 | Development | 0.25
SAL-15 | CRM | Lead & Opportunity Access Control: Each salesperson must only be able to view and manage their own CRM leads and opportunities. Managers must retain full visibility over all leads across the team. | Configuration: Standard Odoo CRM access rights to be configured. Salesperson access level to be set to 'Own Leads Only' in CRM > Settings. Sales Manager role to retain full pipeline visibility across all salespeople. | Phase 1 | Standard
SAL-18 | Sales | Return Management & Editing Window: Returns must be processed at the company where the original sale was made. For a configurable period (currently 3 days from sales order date), the invoice must remain editable and users must be able to reset both the invoice and delivery to draft at line level for partial returns. After this window, editing is locked and all returns require manager approval, processed via credit note and return operation. Only selected users may edit invoices during the return process. | Custom Development: Development required to: - As per SAL-01, we show all invoices/deliveries through smart button - Add a configurable 'Return Window' setting (default 3 days) at the company level - Within the window: allow designated users to reset invoice to draft and reset delivery to draft - After the window: lock all editing on the sales order and invoice; returns only via credit note + return picking with manager approval - Access rights: create a specific user group 'Return Manager' with permission to perform return actions - Visual indicator on the sales order showing whether the return window is open or closed | Phase 1 | Development | 1.5
SAL-20 | Sales | Negative Stock Sales: Selected authorised users must be permitted to confirm sales orders even when stock is insufficient (negative stock). This must be restricted to a configurable list of designated users. | Solution: - Add new group for restriction - Allow negative stock | Phase 1 | Development | 1
SAL-21 | Sales / CRM | New Customer Acquisition Report: Management requires a monthly report showing the number of new customers acquired, grouped by creation month, to track customer growth over time. | Report: Standard Odoo Contacts report to be used with Group By > Created On > Month filter. A favourite filter to be saved in the Contacts module for quick access. Studio: If a more formatted report is required, a Studio report to be created showing new customer count by month with trend visualisation. | Phase 1 | Standard
SAL-22 | Sales / Accounting | Invoice Collection Time Report: Management requires a report showing the elapsed time between invoice date and full payment date for each invoice, enabling analysis of average collection time and payment performance by customer, salesperson, and period. | Custom Development: Two new fields to be added on the customer invoice model (account.move): - 'Fully Paid Date': automatically populated when the invoice payment_state changes to 'paid' (stored field updated via automated action or override of reconciliation method) - 'Days to Pay': computed stored field calculating the difference in days between Invoice Date and Fully Paid Date List view report | Phase 1 | Development | 2
SAL-23 | Sales / Inventory | Slow-Moving Items Report: The system must identify products that have had no significant sales movement within a configurable period, supporting decisions on promotions or stock clearance. | Existing Development: Slow-moving items report is covered by an existing development. To be validated and deployed for Nobel Woods. Configuration: Movement threshold period (e.g. 30/60/90 days with no sales) to be configurable as a parameter on the report. | Phase 1 | Development | 0.5
3. Point of Sale (POS)
POS-01 | POS | Multi-UoM Selling at POS: Cashiers must be able to select the unit of measure for each product at the POS counter. The price must adjust automatically based on the selected UoM and the product's configured conversion factor. | Custom Development: This is an extension of the MD-01 UoM development into the POS module. The POS interface must display a UoM selector per product line. Selecting a different UoM must recalculate the unit price using the product-specific conversion factor defined in MD-01. | Phase 1 | Development |  | Dependent on MD-01 development being completed first
POS-02 | POS | Last Selling Price Display at POS: The POS must display the last selling price for the selected product — both for the specific customer (if identified) and for the customer's pricing tier. | Custom Development: Extension of SAL-04 into the POS interface. Two read-only reference price fields to be displayed on the POS order line: - Last price for this customer and product - Last price for this product within the customer's pricing tier Fields to update dynamically when customer or product is selected. | Phase 1 | Development |  | Consistent with SAL-04 — same development logic extended to POS
POS-03 | POS | VIP & Tier-Based Pricing at POS: The POS must automatically apply the correct pricelist (Retail, Half Wholesale, Wholesale, VIP, Partner) based on the customer selected at time of transaction. | Configuration: Pricelists to be enabled in POS Settings. The POS to be configured to apply the customer's assigned pricelist automatically when a customer is selected at the POS screen. If no customer is selected, the default (Retail) pricelist applies. | Phase 1 | Standard
POS-04 | POS | Minimum Price Enforcement at POS: The POS must enforce the minimum selling price per product. If a cashier attempts to set a price below the minimum, the system must display a manager PIN approval popup before allowing the transaction to proceed. | Custom Development: Extension of SAL-05 into the POS. Development to: - Validate the POS order line price against the product minimum price on every price change - If below minimum: display a manager PIN popup requesting authorisation - Transaction only proceeds after a valid manager PIN is entered - Failed PIN attempts to be logged for audit purposes | Phase 1 | Development |  | Manager PIN configuration to be set up in POS Settings > Restrict Price Modifications
POS-05 | POS | Gift Items at POS: Cashiers must be able to add gift items at the POS. Adding a gift item must trigger a manager approval step (PIN). Gift items must deduct from inventory upon completion of the transaction. | Custom Development: Extension of SAL-07 into the POS. When a product from the Gift Items category is added to a POS order, a manager PIN popup to be triggered before the line is confirmed. Upon session close, gift items to generate standard stock moves consistent with other sold products. | Phase 1 | Development |  | Consistent with SAL-07
POS-06 | POS | Delivery Fee & Driver Commission at POS: Delivery fees must be addable as a service line item during a POS transaction. A configurable percentage of the delivery fee must be automatically allocated as driver commission, consistent with back-office sales logic. | Configuration: Delivery fee service product to be added to the POS product list. Custom Development: Commission allocation logic from SAL-10 to be extended to POS transactions. When a delivery fee is collected via POS and the session is closed and posted, the driver commission amount to be recorded against the driver's analytic account. | Phase 1 | Studio / Dev |  | Consistent with SAL-10
POS-07 | POS | POS Access Restrictions: The following actions must be restricted to authorised users only: refunds and voids, editing product quantities after confirmation, price overrides, and cancellation of completed orders. | Configuration: POS access restrictions to be configured in POS Settings: - Enable 'Restrict Price Modifications' — requires manager PIN - Enable 'Restrict Refunds' — requires manager PIN or specific user role - Configure employee POS roles (Cashier vs. Manager) with appropriate permissions - Void and cancellation actions to require manager PIN | Phase 1 | Standard
POS-08 | POS | Product Search by SKU & Barcode: Cashiers must be able to search and select products at the POS using either the product internal reference (SKU) or a barcode scan. | Configuration: Barcode scanning to be enabled in POS Settings. Products to have their internal reference (SKU) and barcode fields populated during master data setup. POS search bar to support search by product name, SKU, and barcode by default in Odoo 19. | Phase 1 | Standard |  | Barcode hardware (scanner) to be procured by client — confirm device compatibility with Odoo IoT box if required
POS-09 | POS | Salesperson Assignment at POS: Each POS transaction must have a salesperson assigned, selectable from the HR employee list. This enables per-salesperson performance reporting and commission tracking from POS. | Configuration: POS to be configured to display an employee selection screen at the start of each transaction or at session open. Employees to be linked to the POS via the Employees module. Salesperson field on POS order to feed into commission and performance reports. | Phase 1 | Standard
POS-10 | POS | POS Commission Reporting: A report must calculate and display commissions for employees processing sales at the POS, filterable by employee, branch, and period. | Studio: A Studio report to be created on POS orders showing: employee name, total sales amount, number of transactions, commission percentage, and calculated commission amount. Report to support filters by employee, POS session, branch, and date range. | Phase 1 | Studio
POS-11 | POS | Real-Time Sync with Inventory & Accounting: All POS transactions must update inventory stock levels and generate accounting entries upon session close. Full integration between POS, Inventory, and Accounting modules is required. | Configuration: Standard Odoo POS integration with Inventory and Accounting to be activated. POS journal to be configured per company/branch. Stock location for POS to be set to the correct branch warehouse. Session closing to automatically generate the accounting entries and stock moves. | Phase 1 | Standard
4. Procurement & Inventory
INV-01 | Inventory | Warehouse Structure: The company operates 8 warehouses across Iraq shared among Companies A, B, and C. Each warehouse acts as a cost centre for profitability tracking. Internal transfers are used to move products between warehouses. Branch-specific reports and stock visibility must be maintained per warehouse. Companies A, B and C may share the same product but stock must remain company-specific. | Configuration: 32 warehouses to be created in Odoo Inventory > Configuration > Warehouses. Each warehouse to be assigned to the correct company (8 WH per company). Analytic accounts to be created per warehouse/branch for cost centre tracking. Configuration: Internal transfer routes to be configured between warehouses | Phase 1 | Standard
INV-03 | Inventory | Wood Grading Process: Wood products arrive without a confirmed grade breakdown. The actual quantities of Grade A, B, and C are determined only after physical unpacking at the grading warehouse. The system must support a grading operation that reclassifies ungraded stock into the appropriate grade variants. | Solution as a dev: The grading operation occurs at the designated grading/unpacking warehouse location after receipt — not at the initial receipt step. A pop up to set the lot and the grading for that lot (new model for grading) | Phase 1 | Development | 2
INV-04 | Inventory / Accounting | Preliminary & Actual Landed Costs: Before shipment receipt, users must be able to record an estimated landed cost. Product cost must update dynamically based on the estimate. After goods are received, users must be able to reset the preliminary landed cost to draft and re-apply the actual landed cost based on final supplier invoices. | Standard: At the time of delievery create a landed cost. Do not validate it. After invoicing, modify the amounts and validate. This will log a note with the difference. Cusotm Development: Need this to work with SAL-01. Create new model for mock landed cost which should create actual landed cost. | Phase 1 | Development | 3
INV-05 | Inventory / Accounting | Landed Cost Structure: Landed costs consist of: • Customs Duty: 15% of product cost • Import Tax: 3% of product value • Transportation: variable per shipment • Other: loading, port fees, delivery, miscellaneous Each cost type must be tracked separately with a dedicated expense account for P&L visibility. The 15% and 3% amounts must be entered manually — the system must not auto-calculate them. | Landed Cost Structure: Landed costs consist of: • Customs Duty: 15% of product cost • Import Tax: 3% of product value • Transportation: variable per shipment • Other: loading, port fees, delivery, miscellaneous Each cost type must be tracked separately with a dedicated expense account for P&L visibility. The 15% and 3% amounts must be entered manually — the system must not auto-calculate them. | Phase 1 | Standard
INV-06 | Inventory / Logistics | Container & Shipment Tracking: Each import shipment must record: BL number, container number, total weight, total CBM, port status, and shipment stage (Ordered → Shipped → At Port → Customs → Released → Delivered). Reports must be generatable from shipment records. | Development: The following fields to be added to the stock receipt (stock.picking) model using Odoo Studio: - BL Number (Char) - Container Number (Char) - Weight (Float) - CBM (Float) - Port Status (Selection: Ordered / Shipped / At Port / Customs / Released / Delivered) - new Report | Phase 1 | Development | 2
INV-07 | Procurement | Multi-Supplier Configuration: Products must support multiple approved suppliers, each with their own pricing, lead time, and currency. The system must propose the most suitable supplier based on configured price rules during purchase order creation. | Configuration: Multi-supplier configuration to be enabled on each product template (Inventory > Products > Vendor Pricelist tab). Supplier price lists to be populated per product with price, minimum quantity, lead time, and currency. Standard Odoo purchase order creation will propose the preferred supplier based on these rules. | Phase 1 | Standard
INV-08 | Procurement | Vendor Performance Tracking: The system must track vendor performance across: pricing trends, delivery delays vs. committed lead times, and delivery accuracy (qty received vs. ordered). A vendor performance dashboard must be available for procurement managers. | Configuration: Standard Odoo Purchase reporting to be used for vendor performance analysis. Reports available: Purchase Analysis (by vendor, product, price trends) and Receipt Analysis (on-time delivery, quantities). Studio: A vendor performance dashboard to be built using Odoo Studio or Odoo Spreadsheet, consolidating: average lead time vs. actual, delivery accuracy %, and price variance over time. | Phase 1 | Standard
INV-10 | Procurement / Inventory | Monthly Demand Tracking: Management requires visibility of monthly product demand to inform purchasing decisions, including daily demand trends and monthly consumption figures. | Configuration: Standard Odoo Inventory Forecast report to be used with a 30-day time horizon to display daily demand. Monthly demand to be derived from the forecast data. Report: A pivot view on stock moves (filtered to outgoing moves) to be saved as a favourite report showing total quantities moved per product per month. | Phase 1 | Standard
INV-11 | Inventory | Physical Inventory Valuation: During physical inventory counts, the system must display the monetary value of any discrepancy between system quantity and physically counted quantity. Calculated as: Difference in Counted Quantity × Cost Price. | Custom Development: A new computed field to be added to the physical inventory model (stock.inventory or stock.quant in Odoo 19): - Field name: 'Discrepancy Value' - Formula: (Counted Qty − System Qty) × Standard Cost Price of the product - Displayed on the physical inventory screen and included in the inventory adjustment report | Phase 2 | Development | 1
INV-12 | Inventory | Full Inventory Traceability: Full traceability must be maintained from shipment receipt through to warehouse bin location, including lot/serial number tracking, movement history, and the ability to trace a product back to its originating purchase order and shipment. | Configuration: Lot and serial number tracking to be enabled per product category in Inventory Settings. Traceability reports (Inventory > Reporting > Traceability) to be demonstrated to the client. Storage locations and bin locations to be configured per warehouse. | Phase 1 | Standard
INV-13 | Inventory | Barcode Operations: Warehouse operations (goods receipt, internal transfers, picking, delivery) must support barcode scanning. Barcode scanning must also be available via the Odoo mobile application. | Configuration: Barcode module (stock_barcodes) to be activated. Barcode operations to be configured for: receipts, internal transfers, pick operations, and delivery orders. Odoo mobile app to be set up for warehouse staff with barcode scanning enabled. | Phase 1 | Standard
5. Accounting & Finance
ACC-01 | Accounting | Credit Limit & Overdue Duration Enforcement: Each credit customer must have a defined credit limit and overdue duration threshold. Breaching either must block sales order confirmation and trigger a manager approval workflow. This must apply across all sales channels. | Tackled in SAL-08 | Phase 1 | Development | 0
ACC-02 | Accounting | Automated Customer Statements & Payment Reminders: The system must automatically generate and send customer account statements at configurable intervals and send escalating payment reminder emails based on invoice due dates. | Configuration: Odoo Follow-up module (account_followup) to be activated and configured. Follow-up levels to be created: - Level 1: Reminder email at 7 days overdue - Level 2: Second reminder at 15 days overdue - Level 3: Final notice at 30 days overdue Configuration: Email templates per follow-up level to be customised with Nobel Woods branding. Automated follow-up processing to be scheduled (daily automated action). | Phase 1 | Standard
ACC-03 | Accounting / Inventory | Landed Cost Integration with Inventory Valuation: All landed costs applied to import shipments must be automatically allocated to the relevant inventory items and reflected in the product cost, ensuring COGS accurately reflects the total delivered cost. | Configuration: Standard Odoo Landed Costs feature to handle allocation. Allocation method to be agreed per cost type (by quantity, by weight, by volume, or by current cost). Landed cost records to be linked to the relevant stock receipts before posting. Configuration: Inventory valuation method to be set to Average Cost (AVCO) for wood products to ensure landed costs update the product cost correctly. | Phase 1 | Standard
ACC-04 | Accounting | Driver & Salesperson Commission Accounting: Commissions for drivers and salespeople must generate corresponding accounting entries. Driver commissions are based on delivery fees collected. Salesperson commissions are based on fully paid invoice margins. All commission entries must be traceable. | Tackled in SAL-11 and SAL-12 | Phase 1 | Development | 0
ACC-05 | Accounting | Multi-Currency Handling: The system must support multiple currencies for vendor transactions, company operational currency, and management reporting. Exchange rates must be settable at payment level (transactional rate), allowing users to override the system rate at time of payment. | Configuration: Multi-currency to be enabled in Accounting Settings. Currencies (USD, IQD, and others as required) to be activated. Automatic exchange rate update to be configured if available for IQD. Custom Development: Existing dev (needs upgrade): Currency rate on invoices, payment, and misc entries + accounting reports We need to do the following on top of it: Gain/Loss at time of payment to hit specific account (need the business logic here) | Phase 1 | Development | 2
ACC-06 | Accounting | Receivables & Ageing Reports: Detailed accounts receivable reports and ageing analysis showing outstanding balances by customer, age bracket (0-30, 31-60, 61-90, 90+ days), and branch. Reports must be exportable in PDF and Excel. | Configuration: Standard Odoo Accounting > Reporting > Aged Receivable report to be demonstrated and configured. Report to be filtered by branch/company as needed. Configuration: Export to PDF and Excel buttons are standard on all Odoo accounting reports. Report favourites to be saved for quick access by the finance team. | Phase 1 | Standard
ACC-07 | Accounting | Revenue Segmentation Reporting: Revenue must be reportable and filterable by: wood grade, product category, branch/warehouse, company, and salesperson. | Configuration: Analytic accounts and tags to be used for revenue segmentation. Analytic accounts per branch/warehouse to capture location-based revenue. Product categories to be structured to reflect wood grades and product types. Report: Standard Odoo Accounting > Reporting > Profit & Loss with analytic filters to be used for segmented revenue reporting. Odoo Spreadsheet to be used for custom revenue breakdowns if pivot views are insufficient. | Phase 1 | Standard
ACC-08 | Accounting | Custom Tax Based on Weight: A custom tax calculation method is required where tax is computed based on the weight of the product rather than its value. Required for specific product categories subject to weight-based import duties. | Standard Odoo does tax on value (we wont change this) Custom Development: - Add a new checkbox on product called "is import duty" - New button on sale order/invoice called "Add import duty" - This will add the product and calculate the amount (unit price) based on total weight * predefined amount - No tax will be added on this product - We need a predefined amount on import duty | Phase 1 | Development | 1.25 | it will be a line item instead of tax, as tweaking the tax logic in thhe system is a huge process
ACC-09 | Accounting | Invoice Collection Time Report: A report measuring average time between invoice date and full payment date, filterable by customer, salesperson, and period. | Tackled in SAL-22 | Phase 1 | Development | 0
ACC-10 | Accounting / Inventory | Product Cost Visibility Report: Management requires a report showing the approximate landed cost of each product including all sub-variants, reflecting current average cost inclusive of all landed cost components. | Standard: The inventory valuation report in odoo 19 does not show it per product. However, you can see some high level information throough reports in inventory app Custom development: If the standard is not sufficient, we will do a new SQL report (need more info) | Phase 1 | Development | 3.75 | This is huge and the ROI for it is not worth it. shoiuld be dropped
ACC-11 | Accounting | Per-Company Financial Reporting: Each of the 4 companies must have independent financial statements. Consolidated group-level reporting must also be available for management. | Configuration: Each company to have its own chart of accounts configured in Odoo. Standard Odoo financial reports (P&L, Balance Sheet, Cash Flow) are company-specific by default. Configuration: Odoo Consolidation module (if available in Odoo 19 Enterprise) to be activated for group-level consolidated reporting across all 4 companies. | Phase 1 | Standard
ACC-12 | Accounting | Opening Balances: All opening accounting balances must be entered into Odoo prior to go-live. This includes: customer outstanding invoices, vendor outstanding bills, bank balances, and inventory valuation balances per company. | Opening Balance: Opening balances to be entered via journal entries in Odoo Accounting for each company. Outstanding customer invoices and vendor bills to be imported using the standard import utility. Bank balances to be entered as opening entries on the relevant bank journals. Opening Balance: Inventory opening balances (quantities and values) to be entered via the Physical Inventory adjustment tool in Odoo, after the product catalogue and warehouse structure are configured. | Phase 1 | Standard
6. Human Resources
HR-01 | HR | Employee Database: A comprehensive employee database including full personal and professional records, employment contracts, job positions, department hierarchy, and document archiving (IDs, certificates, employment documents). | Configuration: Odoo Employees module to be configured with the company's organisational structure. Departments and job positions to be created. Employee records to be set up for all 25 employees. Master Data: Employee records to be imported using the standard Odoo import template. Employee documents (IDs, certificates) to be uploaded to each employee record in the Documents tab. | Phase 1 | Standard
HR-02 | HR / Attendance | Biometric Attendance Integration (ZKTeco): Employee attendance must be tracked via ZKTeco fingerprint devices. Attendance data must sync automatically with the Odoo Attendance module, handling clock-in/clock-out records and flagging anomalies. | Integration: ZKTeco biometric devices to be integrated with Odoo Attendance using the ZKTeco-Odoo connector. Device communication to be configured (TCP/IP). Attendance records to sync automatically at configurable intervals. Configuration: Odoo Attendance module to be configured with shift schedules and overtime rules. Anomaly detection (missed check-in/out) to be configured using automated actions. Should be a supported device. | Phase 1 | Development | 0.5
HR-03 | HR | Leave Management: Management of all leave types: Annual Leave, Sick Leave, and Unpaid Leave. Employees submit requests via self-service portal, following a configurable approval workflow based on department hierarchy. | Configuration: Odoo Time Off module to be configured with the three leave types: Annual Leave, Sick Leave, and Unpaid Leave. Leave accrual rules to be set per leave type. Configuration: Approval workflow to be configured per department (direct manager approval for standard requests, HR manager for escalations). Employee self-service portal to be activated so staff can submit and track their own leave requests. | Phase 1 | Standard
HR-04 | HR | Contract Management: All employment contracts must be managed in the system including start/end dates, salary details, contract type, and automatic alerts for expiring contracts. | Configuration: Odoo Contracts module (within Employees) to be configured. A contract record to be created for each employee with: contract type, start date, end date, wage, and work schedule. Automated action to be configured to send an alert to HR 30/60 days before contract expiry. | Phase 1 | Standard
HR-05 | HR / Accounting | Payroll Processing: Payroll to be computed based on attendance, leave balances, and contract terms. Support for payroll batch processing, payslip generation, and integration with Accounting for journal entries. | Configuration: Odoo Payroll module to be configured with the company's salary rules, deduction structures, and allowance types. Work schedules to be linked to attendance records for automatic computation. Configuration: Payroll journal to be configured per company to automatically generate accounting entries (debit Salary Expense, credit Salary Payable) upon payroll batch validation. | Phase 1 | Standard
HR-06 | HR | Department Hierarchy & Approval Workflows: Organisational structure with department hierarchies. HR-related approvals (leave, expenses, contract changes) to follow the defined hierarchy. | Configuration: Department structure to be configured in Odoo Employees > Departments. Manager assignments to be set per department. Approval workflows for Time Off and Expenses to be configured to route to the correct manager based on the department hierarchy. | Phase 1 | Standard
HR-07 | HR / General | Every user must be restricted to only the modules and features relevant to their role. Sensitive actions (price overrides, credit approvals, vendor name visibility) must be restricted to designated roles. | Configuration: User roles and access groups to be defined and documented in a User Access Matrix. Each user to be assigned the appropriate access level per module: - Sales: Salesperson / Sales Manager - Inventory: Warehouse Operator / Inventory Manager - Accounting: Accountant / Finance Manager - HR: HR Officer / HR Manager - POS: Cashier / POS Manager Configuration: Custom access groups to be created where standard Odoo roles are insufficient (e.g. Return Manager from SAL-19, Credit Approver from SAL-11). Training: User access matrix to be reviewed and signed off by the client before go-live. | Phase 1 | Standard
HR-08 | HR | Training: HR Module End-user training on: employee record management, leave requests and approvals, attendance review, contract management, and payroll processing. | Training: 2 sessions × 2 hours - Session 1: Employee records, contracts, leave management, attendance review (HR Officers) - Session 2: Payroll processing, batch runs, accounting integration (Finance & HR Managers) Training: All sessions to be recorded and a user manual to be provided. | Phase 1 | Standard
7. Logistics & Fleet
LOG-01 | Logistics / Inventory | Driver Assignment & Delivery Management: Each outbound delivery order must support assignment of a specific driver. Driver assignment must link to the commission calculation logic so delivery fee commissions are automatically attributed to the correct driver. | Tackled in SAL-10 | Phase 1 | Development | 0
LOG-02 | Logistics / Inventory | Container & Shipment Lifecycle Tracking: Each import shipment must be tracked through: Ordered → Shipped → At Port → Customs → Released → Delivered. Shipment records must store BL number, container number, weight, CBM, port status, and expected arrival date. |  | Phase 1 | Development | 0
LOG-03 | Logistics / Inventory | Crane & Truck Service Costing: Crane and truck services used during unloading and delivery must be recorded as service products. Associated costs must be attributable to the relevant shipment or warehouse operation. | Configuration: Crane and truck services to be created as service products in Odoo. These to be added as lines on the relevant vendor bills, linked to the shipment's analytic account for cost tracking. Costs to appear in the shipment profitability report. | Phase 1 | Standard
LOG-04 | Logistics | Fleet Management: Company-owned delivery vehicles to be managed in Odoo Fleet including vehicle records, assigned drivers, service history, and cost tracking per vehicle. | Configuration: Odoo Fleet module to be activated. Vehicle records to be created for each company-owned delivery vehicle with: make, model, licence plate, assigned driver, and insurance details. Service records and fuel logs to be configured for ongoing cost tracking. | Phase 1 | Standard
8. Reporting & Dashboards
RPT-01 | Reporting | Salesperson Performance Dashboard: Real-time dashboard showing per-salesperson KPIs: sales target vs. actual, total collections, commission earned (% only for salesperson view, monetary for manager view), and top products sold. | Custom development: Most fields are already standard, need to make sure the new commission and multi company logic works with this | Phase 1 | Development | 3.5
RPT-02 | Reporting | Product & Grade Analytics: Sales and inventory analysis by product, wood grade (A, B, C), and product dimensions to identify most and least profitable product lines. | Report: Standard Odoo Sales Analysis and Stock reports to be used with Group By filters on product category, variant (grade), and dimensions. Report: Odoo Spreadsheet to be used to build a custom product profitability report combining sales revenue, COGS, and margin per grade and dimension. | Phase 1 | Standard
RPT-03 | Reporting | Wood Stock Ageing Report: A report showing how long specific wood products have been in inventory, by age bracket, to support clearance and promotion decisions. | Custom development: Stock ageing report per lot (since grade is on lot level) | Phase 1 | Development | 1
RPT-04 | Reporting / Inventory | Inventory Valuation Report: Comprehensive inventory valuation showing current stock value per product, per warehouse, and per company, reflecting all landed cost components. | Report: Standard Odoo Inventory > Reporting > Inventory Valuation report to be used. This report shows current stock value per product/variant based on the AVCO cost (inclusive of landed costs). Report: Filters to be saved per company and per warehouse for quick access by the respective teams. | Phase 1 | Standard
RPT-05 | Reporting / Logistics | Delivery Performance Report: Report tracking: on-time delivery rate, average delivery time from order confirmation to delivery, and breakdowns by driver and branch. | Custom development: - Add extra fields - Use normal list view on receipts/delivery | Phase 1 | Development | 0.5
RPT-06 | Reporting / Accounting | Credit & Receivables Dashboard: Real-time view of total outstanding receivables, customers exceeding credit limits, customers with overdue invoices, and ageing breakdown across all branches. | Report: Standard Odoo Accounting > Reporting > Aged Receivable to be used as the primary receivables report. Studio: A management dashboard to be built showing: total AR balance, customers over credit limit (flagged in red), customers overdue beyond threshold, and ageing chart — filterable by company and branch. | Phase 1 | Standard / Studio
RPT-07 | Reporting | Cross-Module Data Export: All reports and dashboards must support export to Excel and PDF. Odoo Spreadsheet must be available for dynamic custom reporting. | Configuration: PDF and Excel export buttons are available by default on all standard Odoo reports. Odoo Spreadsheet to be activated (included in Odoo Enterprise). Key reports to be pre-built and shared as Spreadsheet templates for the finance and management teams. | Phase 1 | Standard
9. System & Access Control